## BookedHours
CITS3200 Project Billed Hours Record for Pranav Rajput Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
2 | 2025-08-01 | 16:00 | 2025-08-01 | 16:45 | First Formal Meeting; Introduce ourselves, set all group meeting agendas, elected Project Manager for Sprint 1. Then we agreed to each make a seed proposal for our Scope of Work in the corresponding shared document by Monday, and on Monday as a Group we'd pick the best one. | 0.75 | 0.75 | 0.75
2 | 2025-08-03 | 9:00 | 2025-08-03 | 9:30 | Working on my Seed Proposal on the Shared Document; Completed the summary of the Project Brief, got part way through the Key Deliverables section. | 0.5 | 1.25 | 0.5
2 | 2025-08-03 | 10:00 | 2025-08-03 | 10:30 | Continued work on my Seed Proposal; Completed deliverables section, made design choices & justifications sections with comprehensive justifications for each choice, partially made overall Tool workflow chart and Proposed System section to complete the Seed Proposal. | 0.5 | 1.75 | 0.5
2 | 2025-08-03 | 22:30 | 2025-08-03 | 22:45 | Finishing my Seed Proposal; Added overall Tool logic flowchart and the Proposed System section. | 0.25 | 2 | 0.25
3 | 2025-08-06 | 17:30 | 2025-08-06 | 18:00 | Meeting #1 with Mentor (Short); Introduced ourselves (and our technical background and university path to this point), discussed Project Brief with the Mentor, came up with and made note of clarifications and questions to bring up with the Client on the Friday (08/08/25) meeting with them, agreed to meet back in 2 weeks when Client meetings had happened and the technical spec was clear, and work has begun then with Sprint 2. | 0.5 | 2.5 | 0.5
3 | 2025-08-07 | 21:15 | 2025-08-07 | 21:45 | Working on the Skills and Resources Audit; Some progress made | 0.5 | 3 | 0.5
3 | 2025-08-08 | 12:00 | 2025-08-08 | 13:30 | Meeting #1 with Client (Long) then short team discussion outside the [UWAOI] building afterwards; Brief significantly clarified; base platform is WebDev (HTML/CSS/jS not Python) with some modules likely required for file handling and ETL in browser (maybe still some Python as a tool for that), Q&A transcript (rough) posted in group chat, will later revise my proposal in light of the findings of the meeting. | 1.5 | 4.5 | 1.5
3 | 2025-08-09 | 16:00 | 2025-08-09 | 16:45 | Revise the Skills and Resources Audit in light of Client Meeting #1; Concept hashed out on a high level, key technologies / platforms / resources identified at the top level summary. | 0.75 | 5.25 | 0.75
3 | 2025-08-09 | 19:45 | 2025-08-09 | 20:30 | Continued work on Skills and Resources Audit; Decided on the structure it would take, breaking down technology/platform seqeuntially with a Function/Required Skill/Required Resource(s) three column table for each to concisely and comprehensively audit it item by item. | 0.75 | 6 | 0.75
4 | 2025-08-11 | 11:00 | 2025-08-11 | 11:45 | Finishing the Skills and Resources Audit; Filled out the Sitecore SXA section after finishing off the Python Tool section. Started the Front End Design section. | 0.75 | 6.75 | 0.75
4 | 2025-08-11 | 14:00 | 2025-08-11 | 15:00 | Finished the Skills and Resources Audit; Finished the Front End Design section and cleaned up errors in the rest of it. Added Final Analysis section to cover what we, in Sprint 1, lack in skills and resources significant to the Project. Added extra bit on where to get the Sitecore skills and resources and the Elsevier PURE RIMS one. | 1 | 7.75 | 1
4 | 2025-08-11 | 16:15 | 2025-08-11 | 16:45 | Revising the Scope of Work; Much more formal structure using UC provided template; Revised to have two parts - Python ETL Tool and Sitecore SXA Theme for the front end; | 0.5 | 8.25 | 0.5
4 | 2025-08-12 | 16:30 | 2025-08-12 | 17:30 | Team meeting for Week 4 before Sprint 1 submissions; Discussed which Scope of Work Proposal to choose, chose Chris Chandra's Scope of Work and took elements (flowchart, design descriptions, etc) of it and other proposals into a single, unified one. We analyzed and made minor changes to the other 4 documents and bundled and zipped them for Project Manager Takumi for Sprint 1 would submit them in the Teams directory and to the Client when the latter had responded about the desired medium to recieve the submission. | 1 | 9.25 | 1
5 | 2025-08-22 | 13:30 | 2025-08-22 | 13:45 | Met with Client; Confirmed to follow up technical questions with Luke Salter (UWA IT rep) to get dev environment access and API token access; Confirmed Java/.NET switch over Python for the back end of the tool. | 0.25 | 9.5 | 0.25
5 | 2025-08-22 | 15:00 | 2025-08-22 | 15:45 | Week 5's Team Meeting; Discussed next steps as part of Sprint 2 and the Project; I (Pranav Rajput) put myself forward as Project Manager for Sprint 2, team concurred; Broke it down into Two Parts: 1) Getting the Sitecore instance setup on our end & getting more familiar with the Platform. 2) Updating the Scope Of Work and Skills and Resources to make the current plan up to date for future guidance. Planned next meeting on Monday 25th Aug, after 1pm. | 0.75 | 10.25 | 0.75
5 | 2025-08-24 | 12:00 | 2025-08-24 | 14:00 | Studied the Sitecore SXA, Java and .NET framework (Java) as agreed on in Week 5's team meeting. Looked into how to get a Sitecore demo instance for free, Windows WSL plus Docker was considered. | 2 | 12.25 | 2
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0